## Requirements
RequirementID | Short Description | Details | Requirement Status (Complete/Incomplete) | Developers Assigned | Developers Who Completed | Standalone/Dependent | Priority | Critical/Not Critical
1 | Login and Authentication | 1.1 - Username: 8 characters exactly, only lowercase | INCOMPLETE | Luke |  | D: Database | 10 | CRITICAL
|  | 1.2 - Password: 12 characters exactly, 1 uppercase, 1 lowercase, 1 numeric, 1 symbol | INCOMPLETE | Luke |  |  | 10 | CRITICAL
|  | 1.3 - display login screen with username and password login | INCOMPLETE | Luke |  |  | 10 | CRITICAL
|  | 1.4 - allow the user to request for a password reset | INCOMPLETE | Luke |  |  | 6 | CRITICAL
|  | 1.5 - lock the users account of 3 incorrect passwords | INCOMPLETE | Luke |  |  | 6 | CRITICAL
2 | Account Types (and interfaces) | Student | INCOMPLETE |  |  | D: Database, Course Catalog, Scheduling Algorithm
|  | 2.1 - can add majors and minors, up to two each | INCOMPLETE | Shane |  |  | 10 | CRITICAL
|  | 2.2 - can enter the number of semesters they would like to graduate in | INCOMPLETE |  |  |  | 8 | CRITICAL
|  | 2.3 - can view or approve proposed schedules | INCOMPLETE | Shane |  |  | 9 | CRITICAL
|  | 2.4 - can modify proposed schedules to account for student preference | INCOMPLETE |  |  |  | 6 | CRITICAL
|  | 2.5 - can request for a coop to occur in a semester specified by the student | INCOMPLETE |  |  |  | 1 | Not Critical
|  | 2.6 - review whether they can finish a degree in a specified number of years | INCOMPLETE |  |  |  | 3 | Not Critical
|  | Faculty Account | INCOMPLETE
|  | 2.7 - can approve majors and minors | INCOMPLETE | Josiah |  |  | 10 | CRITICAL
|  | 2.8 - can approve coops (semester only or year long) | INCOMPLETE |  |  |  | 1 | Not Critical
|  | 2.9 - can approve/reject proposed schedules | INCOMPLETE | Josiah |  |  | 10 | CRITICAL
|  | 2.10 - can provide general comments or approval/denial commments (guidance on whether a student can complete a degree in a specified number of years, why something was approved/denied) | INCOMPLETE |  |  |  | 3 | Not Critical
|  | 2.11 - can approve schedules and schedule changes (waive prerequisites) | INCOMPLETE |  |  |  | 3 | Not Critical
|  | 2.12 - can enter/update account info that is shared with students (name, email, office location) | INCOMPLETE |  |  |  | 2 | Not Critical
|  | Administrator Account | INCOMPLETE
|  | 2.13 - can create student and faculty accounts | INCOMPLETE | Luke |  |  | 10 | CRITICAL
|  | 2.14 - can assign/remove students to faculty | INCOMPLETE | Luke |  |  | 10 | CRITICAL
|  | 2.15 - can remove student and faculty accounts | INCOMPLETE |  |  |  | 6 | CRITICAL
|  | 2.16 - can update usernames and password | INCOMPLETE |  |  |  | 7 | CRITICAL
|  | 2.17 - can update the course catalog | INCOMPLETE |  |  |  | 5 | Not Critical
|  | 2.18 - restore course catalog from backup | INCOMPLETE |  |  |  | 1 | Not Critical
4 | Test Accounts | 4.1 - Minimum of 5 students: | INCOMPLETE | Unassigned |  |  |  | Not Critical
|  | - Student 1: 1 major | INCOMPLETE
|  | - Student 2: 1 major and 1 minor | INCOMPLETE
|  | - Student 3: 1 major and 2 minors | INCOMPLETE
|  | - Student 4: 2 major and 1 minors | INCOMPLETE
|  | - Student 5: 2 majors and 2 minors | INCOMPLETE
|  | 4.2 - Minimum of 3 Faculty: | INCOMPLETE | Unassigned |  |  |  | Not Critical
|  | - Faculty 1 advises 3 students. | INCOMPLETE
|  | - Faculty 1 advises 3 students. | INCOMPLETE
|  | - Faculty 1 advises 3 students. | INCOMPLETE
5 | Scheduling Algorithm (Proposed Schedules) | 5.1 - Schedules need to be broken into Fall and Spring Semester | INCOMPLETE | Josiah |  | D: Account Types, Course Catalog | 9 | CRITICAL
|  | 5.2 - Schedules that include a coop must be extended | INCOMPLETE |  |  |  | 1 | Not Critical
|  | 5.2 - Default credits is 15 per semester. If a student is scheduled for fewer than 11 or greater than 20 credits a flag must be generated and sent to the student and advisor. | INCOMPLETE |  |  |  | 7 | CRITICAL
|  | 5.3 - Schedules must satifsy all course pre-requisites | INCOMPLETE | Josiah |  |  | 9 | CRITICAL
|  | 5.4 - Algorithm should attempt to schedule courses so that the student can graduate in the requested number of semester. If the algorithm determines this is not feasible it should suggest an alternative timeline. The algorithm must also determine how many years (or semesters?) the degree(s) can be completed in. | INCOMPLETE | Shane |  |  | 10 | CRITICAL
|  | 5.5 - algorithm should be able to adjust schedules for coops and provide the same determination on feasible and graduation dates | INCOMPLETE |  |  |  | 2 | Not Critical
6 | Schedule Display | 6.1 - Schedules must be displayed in a calender fashion by semester | INCOMPLETE | Luke |  | D: Scheduling Algorithm | 9 | CRITICAL
|  | 6.2 - Displays graduation date displayed as Semester/Year (Fall 2025) | INCOMPLETE |  |  |  | 3 | Not Critical
|  | 6.3 - Displays graduation date in terms of number of years/semesters to graduation | INCOMPLETE |  |  |  | 6 | CRITICAL
7 | Notifications Tab | 7.1 - Students and faculty are notified of advising assignment | INCOMPLETE |  |  |  | 3 | Not Critical
|  | 7.2 - Students and faculty are notified when credits are above/below threshholds (11/20) | INCOMPLETE |  |  |  | 4 | Not Critical
|  | 7.3 - Faculty are notified when students make changes to their schedules post initial approval | INCOMPLETE |  |  |  | 2 | Not Critical
|  | 7.4 - Students and faculty are notified when schedule changes interfere with graduation timeline | INCOMPLETE |  |  |  | 3 | Not Critical
8 | Course Catalog | 8.1 - Catalog needs to display all courses required for a given degee and their course descriptions | INCOMPLETE |  |  |  | 3 | Not Critical
|  | 8.2 -Administrators can edit the catalog from the admin login interface | INCOMPLETE |  |  |  | 2 | Not Critical
|  | 8.3 - Administrators can upload CSVs for each degree program | INCOMPLETE |  |  |  | 7 | CRITICAL
|  | 8.4 - The system will build course catalog based off of given CSVs | INCOMPLETE |  |  |  | 7 | CRITICAL
9 | Database | 9.1 - The database must store account usernames and password | INCOMPLETE | Josiah |  | Standalone | 10 | CRITICAL
|  | 9.2 - for students it must store name, email, majors, minors, co-ops, graduation year | INCOMPLETE |  |  |  | 2 | Not Critical
|  | 9.3 - for faculty it must store name, email, office location | INCOMPLETE |  |  |  | 2 | Not Critical
Note on F2: Shane Martin: Unassigned is for requirements that we want to implement. Blank means they did not make the top 5.
Note on H2: Shane Martin: Overall dependencies were determined only based on requirements that we intend to implement (priority 8 and above).
Note on J2: Shane Martin: Critical is rated 6-10 priority. Not critical is rated 1-5 priority.
Note on C29: Shane Martin: We decided this entire requirement was non critical because it falls under testing. But we left the details here for when they're needed.

## Top 5
Short Description | Details | Requirement Status (Complete/Incomplete) | Developers Assigned | Developers Who Completed | Standalone/Dependent | Priority | Critical/Not Critical
Login and Authentication | 1.1 - Username: 8 characters exactly, only lowercase | INCOMPLETE | Shane | Shane | D: Database | 10 | CRITICAL | Our top requirements that we intend to implement. They do span 5 different overarching requirements
Login and Authentication | 1.2 - Password: 12 characters exactly, 1 uppercase, 1 lowercase, 1 numeric, 1 symbol | INCOMPLETE | Shane | Shane | D: Database | 10 | CRITICAL
Login and Authentication | 1.3 - display login screen with username and password login | INCOMPLETE | Josiah | Josiah | D: Database | 10 | CRITICAL
Account Types (and interfaces) | 2.1 (student) - can add majors and minors, up to two each | INCOMPLETE | Shane |  | D: Database, Course Catalog, Scheduling Algorithm | 10 | CRITICAL
Account Types (and interfaces) | 2.7 (faculty) - can approve majors and minors | INCOMPLETE | Josiah |  | D: Database, Course Catalog, Scheduling Algorithm | 10 | CRITICAL
Account Types (and interfaces) | 2.9 (faculty) - can approve/reject proposed schedules | INCOMPLETE | Josiah |  | D: Database, Course Catalog, Scheduling Algorithm | 10 | CRITICAL
Account Types (and interfaces) | 2.13 (admin)- can create student and faculty accounts | INCOMPLETE | Luke | Josiah | D: Database, Course Catalog, Scheduling Algorithm | 10 | CRITICAL
Account Types (and interfaces) | 2.14 (admin) - can assign/remove students to faculty | INCOMPLETE | Luke |  | D: Database, Course Catalog, Scheduling Algorithm | 10 | CRITICAL
Scheduling Algorithm (Proposed Schedules) | 5.4 - Algorithm should attempt to schedule courses so that the student can graduate in the requested number of semester. If the algorithm determines this is not feasible it should suggest an alternative timeline. The algorithm must also determine how many years (or semesters?) the degree(s) can be completed in. | INCOMPLETE | Shane |  | D: Account Types, Course Catalog | 10 | CRITICAL
Course Catalog | 9.1 - The database must store account usernames and password | INCOMPLETE | Shane |  | Standalone | 10 | CRITICAL
Account Types (and interfaces) | 2.3 (student) - can view or approve proposed schedules | INCOMPLETE | Shane |  | D: Database, Course Catalog, Scheduling Algorithm | 9 | CRITICAL
Scheduling Algorithm (Proposed Schedules) | 5.1 - Schedules need to be broken into Fall and Spring Semester | INCOMPLETE | Shane |  | D: Account Types, Course Catalog | 9 | CRITICAL
Scheduling Algorithm (Proposed Schedules) | 5.3 - Schedules must satifsy all course pre-requisites | INCOMPLETE | Josiah |  | D: Account Types, Course Catalog | 9 | CRITICAL
Schedule Display | 6.1 - Schedules must be displayed in a calender fashion by semester | INCOMPLETE | Luke |  | D: Scheduling Algorithm | 9 | CRITICAL
Account Types (and interfaces) | 2.2 (student) - can enter the number of semesters they would like to graduate in | INCOMPLETE | Shane |  | D: Database, Course Catalog, Scheduling Algorithm | 8 | CRITICAL
Course Catalog | 8.3 - Administrators can upload CSVs for each degree program | INCOMPLETE | Luke |  | Standalone | 7 | CRITICAL
Course Catalog | 8.4 - The system will build course catalog based off of given CSVs | INCOMPLETE | Luke |  | Standalone | 7 | CRITICAL
Account Types (and interfaces) | 2.16 - can update usernames and password | INCOMPLETE |  |  | D: Database, Course Catalog, Scheduling Algorithm | 7 | CRITICAL
Scheduling Algorithm (Proposed Schedules) | 5.2 - Default credits is 15 per semester. If a student is scheduled for fewer than 11 or greater than 20 credits a flag must be generated and sent to the student and advisor. | INCOMPLETE |  |  | D: Account Types, Course Catalog | 7 | CRITICAL
Login and Authentication | 1.4 - allow the user to request for a password reset | INCOMPLETE |  |  | D: Database | 6 | CRITICAL
Login and Authentication | 1.5 - lock the users account of 3 incorrect passwords | INCOMPLETE |  |  | D: Database | 6 | CRITICAL
Account Types (and interfaces) | 2.4 - can modify proposed schedules to account for student preference | INCOMPLETE |  |  | D: Database, Course Catalog, Scheduling Algorithm | 6 | CRITICAL
Account Types (and interfaces) | 2.15 - can remove student and faculty accounts | INCOMPLETE |  |  | D: Database, Course Catalog, Scheduling Algorithm | 6 | CRITICAL
Schedule Display | 6.3 - Displays graduation date in terms of number of years/semesters to graduation | INCOMPLETE |  |  | D: Scheduling Algorithm | 6 | CRITICAL
Account Types (and interfaces) | 2.17 - can update the course catalog | INCOMPLETE |  |  | D: Database, Course Catalog, Scheduling Algorithm | 5 | Not Critical
Notifications Tab | 7.2 - Students and faculty are notified when credits are above/below threshholds (11/20) | INCOMPLETE |  |  |  | 4 | Not Critical
Course Catalog | 8.3 - Administrators can upload CSVs for each degree program and also edit the catalog from the admin login interface | INCOMPLETE |  |  |  | 4 | Not Critical
Account Types (and interfaces) | 2.6 - review whether they can finish a degree in a specified number of years | INCOMPLETE |  |  | D: Database, Course Catalog, Scheduling Algorithm | 3 | Not Critical
Account Types (and interfaces) | 2.10 - can provide general comments or approval/denial commments (guidance on whether a student can complete a degree in a specified number of years, why something was approved/denied) | INCOMPLETE |  |  | D: Database, Course Catalog, Scheduling Algorithm | 3 | Not Critical
Account Types (and interfaces) | 2.11 - can approve schedules and schedule changes (waive prerequisites) | INCOMPLETE |  |  | D: Database, Course Catalog, Scheduling Algorithm | 3 | Not Critical
Schedule Display | 6.2 - Displays graduation date displayed as Semester/Year (Fall 2025) | INCOMPLETE |  |  | D: Scheduling Algorithm | 3 | Not Critical
Notifications Tab | 7.1 - Students and faculty are notified of advising assignment | INCOMPLETE |  |  |  | 3 | Not Critical
Notifications Tab | 7.4 - Students and faculty are notified when schedule changes interfere with graduation timeline | INCOMPLETE |  |  |  | 3 | Not Critical
Course Catalog | 8.1 - Catalog needs to display all courses required for a given degee and their course descriptions | INCOMPLETE |  |  |  | 3 | Not Critical
Account Types (and interfaces) | 2.12 - can enter/update account info that is shared with students (name, email, office location) | INCOMPLETE |  |  | D: Database, Course Catalog, Scheduling Algorithm | 2 | Not Critical
Scheduling Algorithm (Proposed Schedules) | 5.5 - algorithm should be able to adjust schedules for coops and provide the same determination on feasible and graduation dates | INCOMPLETE |  |  | D: Account Types, Course Catalog | 2 | Not Critical
Notifications Tab | 7.3 - Faculty are notified when students make changes to their schedules post initial approval | INCOMPLETE |  |  |  | 2 | Not Critical
Course Catalog | 8.2 -Administrators can edit the catalog from the admin login interface | INCOMPLETE |  |  |  | 2 | Not Critical
Database | 9.2 - for students it must store name, email, majors, minors, co-ops, graduation year | INCOMPLETE |  |  | Standalone | 2 | Not Critical
Database | 9.3 - for faculty it must store name, email, office location | INCOMPLETE |  |  | Standalone | 2 | Not Critical
Account Types (and interfaces) | 2.5 - can request for a coop to occur in a semester specified by the student | INCOMPLETE |  |  | D: Database, Course Catalog, Scheduling Algorithm | 1 | Not Critical
Account Types (and interfaces) | 2.8 - can approve coops (semester only or year long) | INCOMPLETE |  |  | D: Database, Course Catalog, Scheduling Algorithm | 1 | Not Critical
Account Types (and interfaces) | 2.18 - restore course catalog from backup | INCOMPLETE |  |  | D: Database, Course Catalog, Scheduling Algorithm | 1 | Not Critical
Scheduling Algorithm (Proposed Schedules) | 5.2 - Schedules that include a coop must be extended | INCOMPLETE |  |  | D: Account Types, Course Catalog | 1 | Not Critical
Account Types (and interfaces) | Student | INCOMPLETE |  |  | D: Database, Course Catalog, Scheduling Algorithm
Account Types (and interfaces) | Faculty Account | INCOMPLETE |  |  | D: Database, Course Catalog, Scheduling Algorithm
Account Types (and interfaces) | Administrator Account | INCOMPLETE |  |  | D: Database, Course Catalog, Scheduling Algorithm
Test Accounts | 4.1 - Minimum of 5 students: | INCOMPLETE | Unassigned |  |  |  | Not Critical
Test Accounts | - Student 1: 1 major | INCOMPLETE
Test Accounts | - Student 2: 1 major and 1 minor | INCOMPLETE
Test Accounts | - Student 3: 1 major and 2 minors | INCOMPLETE
Test Accounts | - Student 4: 2 major and 1 minors | INCOMPLETE
Test Accounts | - Student 5: 2 majors and 2 minors | INCOMPLETE
Test Accounts | 4.2 - Minimum of 3 Faculty: | INCOMPLETE | Unassigned |  |  |  | Not Critical
Test Accounts | - Faculty 1 advises 3 students. | INCOMPLETE
Test Accounts | - Faculty 1 advises 3 students. | INCOMPLETE
Test Accounts | - Faculty 1 advises 3 students. | INCOMPLETE
Note on D1: Shane Martin: Unassigned is for requirements that we want to implement. Blank means they did not make the top 5.
Note on F1: Shane Martin: Overall dependencies were determined only based on requirements that we intend to implement (priority 8 and above).
Note on G1: Shane Martin: We determined the requirements we intend to implement based on priority. We broke it down to subpriority to better manage the workload within each overarching requirement.
Note on H1: Shane Martin: Critical is rated 6-10 priority. Not critical is rated 1-5 priority.
Note on A49: Shane Martin: We decided this entire requirement was non critical because it falls under testing. But we left the details here for when they're needed.